## Sheet1
S.No. | VIOLATION ID | CLASS | ORDER # | APT # | STORY # | VIOLATION DESCRIPTION | REPORTED DATE | NOV ISSUED DATE | NOV ID | NOV TYPE | CORRECTION BY DATE | CERTIFICATION BY DATE | VIOLATION STATUS | VIOLATION STATUS DATE | ACTUAL CERT. DATE
1 | 18073133 | B | 502 | 2A | 3 | § 27-2005 adm code properly repair with similar material the broken or defective wood floor located at b-room 2a, 3rd story, 1st b-room from south at west | 2025-06-25 | 2025-07-03 | 9894046 | ORIGINAL | 2025-08-07 | 2025-08-21 | NOV SENT | 2025-07-03 | -
4 | 18073188 | B | 508 | 2A | 3 | § 27-2005 adm code repair the broken or defective plastered surfaces and paint in a uniform color all walls and ceiling located at b-room 2a, 3rd story, 1st b-room from south at west | 2025-06-25 | 2025-07-03 | 9894046 | ORIGINAL | 2025-08-07 | 2025-08-21 | NOV SENT | 2025-07-03 | -
2 | 18073161 | B | 502 | 2B | 3 | § 27-2005 adm code properly repair with similar material the broken or defective wood floor located at b-room 2b, 3rd story, 1st b-room from west at north | 2025-06-25 | 2025-07-03 | 9894044 | ORIGINAL | 2025-08-07 | 2025-08-21 | NOV SENT | 2025-07-03 | -
3 | 18073176 | B | 508 | 2B | 3 | § 27-2005 adm code repair the broken or defective plastered surfaces and paint in a uniform color all walls and ceiling located at b-room 2b, 3rd story, 1st b-room from west at north | 2025-06-25 | 2025-07-03 | 9894044 | ORIGINAL | 2025-08-07 | 2025-08-21 | NOV SENT | 2025-07-03 | -
14 | 18073248 | B | 506 | 2B | 3 | § 27-2005 adm code replace with new the missing firestopping material at entire open ceiling area located at b-room 2b, 3rd story, 1st b-room from west at north | 2025-06-25 | 2025-07-03 | 9894044 | ORIGINAL | 2025-08-07 | 2025-08-21 | NOV SENT | 2025-07-03 | -
15 | 18073747 | B | 510 | 2B | 3 | § 27-2005 adm code & 309 m/d law abate the nuisance consisting of firestopping material at ceiling located at b-room, 3rd story, 1st b-room from west at north | 2025-06-25 | 2025-07-07 | 9896040 | ORIGINAL | 2025-08-11 | 2025-08-25 | NOV SENT | 2025-07-07 | -
5 | 18073197 | B | 502 | 3A | 4 | § 27-2005 adm code properly repair with similar material the broken or defective wood floor located at b-room 3a, 4th story, 1st b-room from south at west | 2025-06-25 | 2025-07-03 | 9894043 | ORIGINAL | 2025-08-07 | 2025-08-21 | NOV SENT | 2025-07-03 | -
6 | 18073201 | B | 508 | 3A | 4 | § 27-2005 adm code repair the broken or defective plastered surfaces and paint in a uniform color all walls and ceiling located at b-room 3a, 4th story, 1st b-room from south at west | 2025-06-25 | 2025-07-03 | 9894043 | ORIGINAL | 2025-08-07 | 2025-08-21 | NOV SENT | 2025-07-03 | -
7 | 18073214 | B | 502 | 4A | 5 | § 27-2005 adm code properly repair with similar material the broken or defective wood floor located at b-room 4a, 5th story, 1st b-room from east at south | 2025-06-25 | 2025-07-03 | 9894047 | ORIGINAL | 2025-08-07 | 2025-08-21 | NOV SENT | 2025-07-03 | -
8 | 18073221 | B | 508 | 4A | 5 | § 27-2005 adm code repair the broken or defective plastered surfaces and paint in a uniform color all walls and ceiling located at b-room 4a, 5th story, 1st b-room from south at west | 2025-06-25 | 2025-07-03 | 9894047 | ORIGINAL | 2025-08-07 | 2025-08-21 | NOV SENT | 2025-07-03 | -
9 | 18073229 | B | 502 | 4C | 5 | § 27-2005 adm code properly repair with similar material the broken or defective wood floor located at b-room 4c, 5th story, b-room at east | 2025-06-25 | 2025-07-03 | 9894048 | ORIGINAL | 2025-08-07 | 2025-08-21 | NOV SENT | 2025-07-03 | -
10 | 18073230 | B | 508 | 4C | 5 | § 27-2005 adm code repair the broken or defective plastered surfaces and paint in a uniform color all walls and ceiling located at b-room 4c, 5th story, 1st b-room from north at east | 2025-06-25 | 2025-07-03 | 9894048 | ORIGINAL | 2025-08-07 | 2025-08-21 | NOV SENT | 2025-07-03 | -
11 | 18073242 | B | 502 |  | 3 | § 27-2005 adm code properly repair with similar material the broken or defective slopping wood floor at public hall, 3rd story | 2025-06-25 | 2025-07-03 | 9894045 | ORIGINAL | 2025-08-07 | 2025-08-21 | NOV SENT | 2025-07-03 | -
12 | 18073245 | B | 502 |  | 4 | § 27-2005 adm code properly repair with similar material the broken or defective slopping wood floor at public hall, 4th story | 2025-06-25 | 2025-07-03 | 9894045 | ORIGINAL | 2025-08-07 | 2025-08-21 | NOV SENT | 2025-07-03 | -
13 | 18073246 | B | 502 |  | 5 | § 27-2005 adm code properly repair with similar material the broken or defective slopping wood floor at public hall, 5th story | 2025-06-25 | 2025-07-03 | 9894045 | ORIGINAL | 2025-08-07 | 2025-08-21 | NOV SENT | 2025-07-03 | -